Sample Project Planning Timeline

(2-Week Project)

| Date | Time | Action and/or Activity | Responsible | Resources | Location | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 18Mar | 4:00PM | Team After Action Review for project (1 hour) | All | Coordinate Room (Mike) | FH 251B |  |
| 17Mar | 11:00AM | Turn in project | Leader |  | FH341 |  |
| 16Mar | 3:00PM | Final In-Progress Review (IPR) of project deliverables (45 minute meeting) | All | *Coordinate Room (Mike) *Final print (Pat) | FH A17 |  |
| 15Mar | 8:00PM | Synthesize comments on draft, conduct final edits, and post final document on Google Drive | Beth |  | Google Drive |  |
| 15Mar | 1:00PM | Final comments on project draft completed | All |  | Google Drive |  |
| 14Mar | 9:00PM | Team Leader creates and sends out/post agenda for final In-Progress Review Meeting and identifies pre-work | Leader |  | Google Drive |  |
| 14Mar | 7:00 PM | Final drafts completed and posted on Google Drive Team members begin their final review and post comments on products | All All |  | Google Drive |  |
| 12Mar | 9:00PM | Second In-Progress Review via WEBEX (45 minutes) Dial in number: 688-709-2427 Access code: 780-957-2378 | All | Computer |  |  |
| 12Mar | 1:00PM | Review comments completed on first draft of requirements Team Leader reviews comments and creates agenda for second in-progress review and sends/post to members | All | Coordinate WEBEX (John) | Google Drive |  |
| 11Mar | 9:00 PM | First draft of requirements posted on Google Drive All team members begin review of first draft of requirements and post comments and suggestion in the document | All All |  | Google Drive |  |
| 8Mar | 5:00 PM | First In-Progress Review (45 minute meeting) -each member briefs status of progress on responsibilities -adjust process and allocations as needed -determine if you need additional resources -revisit timeline | Leader |  | FH 251B |  |
| 6 Mar | 8:00 AM | Team Leader sends out agenda and location for first In-progress review and identifies any pre-work | Leader | Coordinate Room (Mike) | FH251B |  |
| 5 Mar | 5:00 PM | Initial Team Project Planning Meeting -ensure all understand scope of project requirements and standards of success -brain storm on how best to complete project - allocate roles and responsibilities -identify deliverables and deadlines -refine project timeline (2.5 hours) Meetings and deadline from project timeline posted to Team’s Calendar | All George |  | FH 351 Google Drive |  |
| 4 Mar | 8:00 PM | *Team Leader creates and sends/posts agenda (with purpose, outcomes, and time limit) for initial planning meeting, identifies pre-work, and tentative project timeline | Leader |  | Google Drive |  |
| 4 Mar | 3:00 PM | *Received Project and set time for initial planning meeting. *Coordinate room for initial team meeting *All members review requirements, deliverables, conduct research, and develop a tentative plan to complete the project | All | Coordinate Room (Mike) Copies of project requirements | FH351 |  |